## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
3 | Implementaçâo das funcionalidades | 1 | 1
1 | Report a explicar as metricas | 1 |  | 1 | 1
2 | Testes unitarios | 1 |  | 1
4 | Use Cases | 2 |  |  | 1 | 1
5 | Video | 1
Completed Effort |  | 0 | 1 | 2 | 2 | 1 | 0
Remaining Effort |  | 6 | 5 | 3 | 1 | 0 | 0
Ideal Burndown |  | 6 | 4.8 | 3.6 | 2.4 | 1.2 | 0