## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Estudar aplicação | 2 | 1 | 1
2 | Brainstorm | 2 |  |  | 1 |  | 1
3 | Escolher 2 ideias a implementar | 1 |  |  | 1 |  | 1
4 | Submeter Trabalho | 1 | 1
Completed Effort |  | 0 | 2 | 1 | 2 | 0 | 2
Remaining Effort |  | 6 | 4 | 3 | 1 | 1 | -1
Ideal Burndown |  | 6 | 4.8 | 3.6 | 2.4 | 1.2 | 0