## Burndown Chart
Sprint Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-11-21 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
3 | Implementaçâo das funcionalidades | 1 | 1
1 | Report a explicar as metricas | 1 |  | 1
2 | Testes unitarios | 1 |  | 1
Completed Effort |  | 0 | 1 | 2 | 0 | 0 | 0
Remaining Effort |  | 3 | 2 | 0 | 0 | 0 | 0
Ideal Burndown |  | 3 | 2.4 | 1.8 | 1.2 | 0.6 | 0